## Work Plan - Example A
School Name: School X | Note: This work plan is provided as an example. It is representative of a more complex project. See the second tab for an example of a simpler project |  | Timeline Key Milestones: Sept 2022- June 2024
Activity | Short Description | Who is Responsible | Start Date | End Date
Monitoring, recording progress and celebrating | video/visual documentation of overall project | School Board Communications Dept. |  | ongoing
Monitoring, recording progress and celebrating | Monthly Board Environmental Sustainability meeting report out of farm goals and actions | Farm Project Lead |  | monthly ongoing
Infrastructure | Establish fencing, irrigation, soil | School Board | Summer 2022
Planning | Crop schedule meeting with Farmer, culinary arts program teachers to set up a fall crop schedule for purposes of integrating food into school teaching | School Board | 2022-08-01
Planning | School wide staff meeting introducing farmer to staff | School Board | Sept. 2022
Planning | 9 School Board Learning Coordinators welcomed on site, and begin work to add resources and curricular supports for schools to School Board's resource content | School Board Learning Coordinators | Sept. 2022 | ongoing
Celebration | Official Farm Launch Event | School Board, Community Partner Lead | Sept. 2022
Farming | Farmer establishes Fall crop, inital workshops with some classes | Farmer "Stu Hopps" (from Young Agrarians partnership | Sept. 2022 | 2022-11-01
Food Distribution | Pilot the distribution of food growing on site to schools and students | School Board, School Foundation | 2022-10-01 | 2022-12-01
Infrastructure | Install produce wash station | School X | 2022-10-01
Infrastructure | Trades students build 3 bin compost system on site | School X | 2022-10-01
Planning | School staff meeting check-in, establish spring schedule | School X | 2022-12-01
Infrastructure | Trades student build greenhouse on site | School X | 2023-01-01
Fundraising | Apply for Canada Summer Youth Works funding | School Board, Community Partner Lead | 2023-01-01
Evaluation and Reporting | Report on Farm activities and business given at public board meeting. This supports further investment by the school district and ongoing policy development that establishes future food literacy infrastructure in the School Board schools. | Project Lead | 2023-01-01
Farming | Planting begins for spring | School Farmer | 2023-02-01
Professional Development | Provinicial and school-based ProD opportunity to promote the farm, and for Teachers to provide feedback on curricular connections to the farm | Farmer "Stu Hopps" (from XXXXX partnership, learning coordinators, project partners) | 2023-02-01
Infrastructure | Trades students build garden shed on site | School X | 2023-04-01
Farming | Summer student hired | School Board | 2023-05-01
Farming | Summer student support farmer | School Farmer | 2023-06-01
Celebration | Community Farm Celebration. Refelection and visioning meeting for systems established in year 1, and intend priorities for the coming year. Evaluate our work. Set new goals for Year 2. Invite neighbourhood and share food. | Project Lead and team | 2023-06-01
Professional Development | School-based staff ProD opportunity to promote the farm, and for Teachers to provide feedback on curricular connections to the farm | Farmer "Stu Hopps" (from XXXXX partnership, learning coordinators, project partners) | 2023-06-01
Planning | Year 2: Farmer and School staff re- establish student involvement in farm. Farmer and culinary arts programs tweak planting schedule. | Project lead and team | Sept. 2023
Curriculum | create locally developed high school credit school farm course | Resource Teachers across the District | Sept. 2023
Planning | Farmer establishes Fall crop, inital workshops with some classes | School Board learning coordinators, and Farmer "Stu Hopps" (from XXXX partnership) | Sept. 2023
Farming | Farm establishes Fall crops |  | Sept. 2023
Fieldtrips | Invitation for schools across District to become more involved on site. Fieldtrips to Farm. |  | Sept. 2023 | 2023-12-01
Professional Development | Provinicial and school-based ProD opportunity to promote the farm, and for Teachers to provide feedback on curricular connections to the farm | Farmer "Stu Hopps" (from XXXXX partnership, learning coordinators, project partners) | 2023-10-01
Evaluation and Reporting | Report on Farm activities and business given at public board meeting. This supports further investment by the school district and ongoing policy development that establishes future food literacy infrastructure in the School Board region. | Project lead and team | 2024-01-01
Curriculum | Pilot first semester of School Farm Course | School Board Teacher, support staff | 2024-02-01 | 2024-04-01
Professional Development | Provinicial and school-based ProD opportunity to promote the farm, and for Teachers to provide feedback on curricular connections to the farm | Farmer "Stu Hopps" (from XXXXX partnership, learning coordinators, project partners) | 2024-02-01
Evaluation and Reporting | Meeting between farmer and District staff to review two years of activities and progress | Project lead and team | 2024-06-01
F2CC Reporting | Collect photos, resources, and other materials. Complete writing for final F2CC report | Community Partner and School Board | 2024-06-01

## Work Plan - Example B
School Name: School Y | Note: This work plan is provided as an example. It is representative of a simpler project. See the first tab for an example of a more complex project |  | Timeline Key Milestones: Sept 2022- June 2024
Activity | Short Description | Who is Responsible | Start Date | End Date
Freezer Purchase | Order chest freezer from Leons | Project Lead with help of Secondary Contact & Community Partner | June 2022 | June 2022
Salad Bar Tray Rail Purchase | Order from XXXXX | Project Lead with help of Secondary Contact & Community Partner | May 2022 | May 2022
Microgreen kits | Order from ABC Local Seed Company | Project Lead with help of Secondary Contact & Community Partner | May 2022 | May 2022
Resouces for microgreen growing and taste testing | Collate existing resources from Partner A and Partner B, and make new ones if necessary | Teacher team with help of Community Partner | June 2022 | Oct 2022
Hydroponic set up, growing, curriculum | Order Tower Garden; attend online training | Project Lead with help of Secondary Contact & Community Partner; teacher team | June 2022 | Oct 2022
Protective barrier for tower garden | Select location in school foyer, measure and build and/or purchase, tech students to assist process | Project lead & teacher team | Sept 2022 | Oct 2022
Memorandums of Understanding | Taking into cosideration provincial procurment policy, public health guidelines and cafeteria menu, work with local farms to grow select produce | Project lead & Community partner with input from students of the teacher team | May 2023 | June 2024
Promotion of grant and farm to school activities | Social media,school newsletters, website | Students under supervision of teacher team | May 2022 | Ongoing
Organize/schedule after school Kitchen Brigade | Promote/recruit, ensure necessary school permissions are completed, participatory menu creation | Project lead | Sept 2022 | June 2024
Kitchen Brigade student kit collation | Source supplies from ABC Kitchen (local kitchen store) and other stores, staying within budget | Project lead | Sept 2022 | Sept 2022
Facilitate Kitchen Brigade | Facilitate after school club | Secondary contact with help of community partner | Oct 2022 | June 2024
Share project opportunities/ideas with school staff | Via inservice days and staff communications share Tower Garden, microgreen and Big Crunch activities to compliment curriculum | Project lead, secondary contact, & teacher team | June 2022 | Ongoing
Create and taste test menu for school-wide meal | African student club will collate recipes, test and work with head chef to scale up | Project lead, commmunity partner, African student club | Sept 2022 | January 2023
Volunteers for celebratory meal | Draw from PTA and Program ABC volunteers | Project lead and Community partner | Jan 2023 | Feb 2023
Field trips to Partner C and Farmer D | Based on Kitchen Brigade and student club activities time line | Secondary contact and teacher team | Fall 2023 | June 2024
Lunch Menu Schedule | Work with identified partners to incorporate seasonal produce and new recipes | Project lead, secondary contact & teacher team | June 2022 | Ongoing

## Budget
Item | Description of Item | Amount requested from Farm to Cafeteria Canada | (Optional) Amount available from other sources (include cash or in-kind contributions amount and source)
Honoraria Nominal, one-time recognition for community partners who provide support in project initiation, food service preparation or connecting students to the local food system (Recommended range: up to 10% of the total grant funds) |  |  | Pending funding: Indigenous Leadership (2 workshops) $1000
Community partnerships A portion of the funds may be earmarked to bring community partners to the table – individuals who can provide additional expertise and technical training/resources to ensure the proposed program is tied to and supports the sustainability of the local food system. (Recommended range: up to 15% of the total grant funds) | A 'School Farm' Advisory that includes technical advice, urban planning and policy guidelines for the design and infrastruture of the school farm. We have had initial discussions with potential Advisory members included in regional government, non-profits, farmers, and indigenous leaders. Some of the roles will not require an honorarium for participation (such as local government representatives), but other's committement to the advisory will. | $1,000.00 | Community foundation: $1,500 funding, $1,500 in kind, XXX Bank: $500 (pending)
Training - to build the knowledge and capacity of school-based project team members. These funds can be used toward training offered by F2CC, its regional partners*, conferences, or other learning opportunities We recommend reserving 5-15% of the total grant funds for training and educational opportunities of your team. | Teacher/administrative/Special Education Assistant release time in order to attend professional development, essential meetings. Course fees, including any necessary travel could be used for this budget item. |  | In kind support from School District
Training - to build the knowledge and capacity of school-based project team members. These funds can be used toward training offered by F2CC, its regional partners*, conferences, or other learning opportunities We recommend reserving 5-15% of the total grant funds for training and educational opportunities of your team. *Training offered may vary by region. | Compost material set up: $3000 Commerical Refridgerator: $3000 Produce Wash Station: $2000 Farm Tools for students: $1000 | $9,000.00 | Community foundation: $10,000 provided to seed the development and other infrastructure of this farm
Equipment Can include the following: Kitchen equipment at the school such as refrigerators, freezers, salad bar units, food warmers, food processors, soup pots, dishes, cutlery, storage bins, cutting boards, knives, soap and towel dispensers, etc. Equipment and material costs for the growing of food such as seeds, soil, lumber, garden tools, composting unit, greenhouse materials, etc. Recommendation: not to exceed $3,000 of the grant funds for a single piece of equipment. | Installation of a new refrigerator
Space modification For minor food service space upgrades for food service spaces. Recommendation: not to exceed $3,000 of grant funds.
Promotional & Educational Supplies
Food for initial celebratory meal service Schools may allocate a maximum of 20% or up to $2,000 toward purchasing food. |  | N/A
Food following the initial start up |  | $10,000.00 | $14,500.00
Estimated TOTAL program cost (including all funding sources and in-kind contributions) for the grant period (though June 2024): | $24,500.00

## Food Sources
Where will you source local food for your program?
Supporting local producers including farmers, fishers, hunters, harvesters and/or others participating in the local food system is an important part of the Farm to School Canada Grants. All grant recipients will be expected to engage local food providers – either directly or through the local food supply chain – in order to purchase foods for the school meal service. Community partners can assist schools with the task of sourcing, procuring, preparing and serving local foods.
Please note: while a school garden complements and is a strong addition to farm to school program, increasing food literacy and increasing access to food that students have grown themselves in school meals, it is not a substitute for a local food producers or suppliers.
Food Source | Check all that Apply (Yes or No) | Name of farm/ business/ supplier/ organization you will source from
Farmer / Farmers’ Market | Yes | See "other"
Community /Market Garden | No
Fisher, hunter or wild food harvester | No
School Garden / School Greenhouse | Yes | This project will help support the the development of a productive on-school farm. We hope to work with a local farmer and supply fresh produce to our school and eventually, neighbouring schools.
Food Distributor | No
Grocery Store | No
Other | Yes | Our partner program does source food from local food banks, businesses and has grant funding to purchase through local organizations such as additional farms in our community.

## Team Roles & Responsibilities
Who will be involved? Please identify the members of your project team by completing the following table.
TIP: Successful programs are created and supported by strong community relationships and a committed team of people. We have identified typical core team members with an (*), along with their potential roles in the table below. Many options of additional people who typically comprise a farm to school team are also provided, should you wish to include them.
Note: We recognize that team members and their roles will vary depending on the specific context and that, in some cases, one individual may represent more than one ‘team member.’ For example, the principal or vice-principal is the lead applicant, and they may also be the Farm to School Program Coordinator.
Team member | Name(s) and email | Roles and responsibilities
The following are required team members for all applications
* Principal or Vice Principal (Lead Applicant) Provides leadership and program oversight. Ensures program funds are administered and deliverables are met, on time and on budget. | Chief Bogo bogo@gmail.com | Project Lead District Principal of Environmental Stewardship. Oversee and monitor the full program. Collect relevant data based on school food, curricular/learning activities and environmental goals and actions intended for this project. Lead collaboration between all individuals and groups associated with the farm. Ensure appropriate goal setting and celebration of success. Document the aspects of the project. Manage the project budget.
*Community Partner Ensures the proposed program is tied to and supports the sustainability of the local food system. Provides additional expert technical support to the school community to realize program vision, goals and deliverables. | Nick Wilde (community partner organisation X) nick@gmail.com | Nick is the Executive Director of "Community Partner Organisation X", which runs the "Healthy Food for Schools program". This program provides the meal distribution that happens from the district-level. "Healthy Food for Schools X" has created a food depot to allow them to access donated food, bulk purchase, sort, store and deliver to schools across the District. They work directly with all schools to help them provide healthy meals and snacks to vulnerable students. Programs may include breakfast, lunch and/or snacks
*Community Partner B Program Coordinator Coordinates the day-to-day school-based activities of the proposed programs (can be the same as the food service lead). | Bellwether bellwether@gmail.com | Ensure technical, administrative, and network support towards school farm.
*Food Service Lead Coordinates the meal service component of the grant. | Priscilla (Community Schools Coordinator) priscilla@gmail.com | Liaise with school food programs providers and teacher and farmer to ensure food grown at the farm is being utilized and meeting needs. Organize the procurement of produce grown on the farm. Supports the farm project through fundraising, securing volunteers, etc.
The following are optional additional team members applicants may wish to include.
Parent Council/School Council Representative Supports program through fundraising, securing volunteers, etc. | Officer Clawhauser (School Board X Environmental Sustainability Committee) clawhauser@gmail.com | School Trustee & Chair of Board of Education Environmental Stewardship Committee: Monitor farm goals and progress. Report out to other trustees. Ability to initiate dialogue and actions at the Board level, in relation to the farm and its intended goals and actions.
Farmers or other local food providers Produces or providers foods for the proposed program. May also be engaged in supporting hands-on learning opportunities for students. Tip: support from local farmers, fishers, harvesters or other food system actors can be integral to program success. Connect early in your program planning process and extend an invitation to be a part of your team | Fru Fru (Young Agrarians Land Matcher, Region X) frufru@gmail.com | A farmer partnership is currently being sought with support from Young Agrarians. A farmer will be a primary partner for the school farm, and will have a 3 yr partnership contract with the district to being the relationship. Roles the farmer will play include input and development of school farm infrastructure, food production decisions, and collaboration in developing school program involvement on site. The farmer will be the primary stakeholder in the technical decisions of farm maintenance and food growing.
Environmental Health Officer or Public Health Inspector Reviews and approves the proposed program with a food safety lens. EHO/PHI support is integral to program success. We encourage connecting with your EHO/PHI early, and to extend an invitation to be part of the team. | Judy Hopps (Regional Health Authority Organization) judy@gmail.com | The "Regional Health Authority Organization" is providing consultation to the School Farm project. Judy will be providing an overview of any food safety considerations for space design and infrastructure for food washing and handling in the farm space. Once food is transferred to processing inside the school, the "School Foundation" will take over food handling with their already-existing food safety protocols and procedures.
Students
Teachers
Gardeners
Elders or traditional knowledge keepers | Mrs. Otterton otterton@gmail.com Nangi nangi@gmail.com | Ensure and support farm projects and associated actions align with the School District X Reconciliation policy and framework.
Chefs/culinary arts instructors
Community Nutritionist or Public Health Dietitian | Bonnie Hopps bonne@gmail.com | Bonnie is on the Public Health Advisory Committee and her role supports consultation with schoool-related projects in the region.
Others |  | School Board X Environment Sustainability Committee: groups represented on this committee are: school parent groups, student reps, local unions, Indigenous reps and school district staff from various departments